## Risk Register
UK Move - Decision Risk Register (side by side)
Impact x Probability, 1-5 each (Score = I x P, 1-25). Green <=6, Amber 7-12, Red >=15. Scores are STARTING ESTIMATES for Julian to adjust - this is a judgment tool, not a verdict. Rows tagged [JH] carry Julian's own risk-acceptance. 11 Jul 2026.
Category | Risk | London-direct |  |  | Malvern crash-pad interim |  |  | Stay-HK (TTI lifeline) |  |  | Key mitigation | Residual / Julian's judgment
|  | I | P | Score | I | P | Score | I | P | Score
Financial | Run out of money in the search → forced early pension/MPF drawdown | 4 | 4 | 16 | 4 | 2 | 8 | 2 | 2 | 4 | Bank the £12,475 rebate (+pot); floor job early ~£77k; MPF as backstop | London's central risk (tight ~£50-56k pot ~11-12mo); Malvern's runway defuses it
Financial | Long search at 55 (ageism) outlasts the runway | 4 | 3 | 12 | 3 | 2 | 6 | 2 | 2 | 4 | Niche-lane discipline; long Malvern runway; take a floor job then trade up | Malvern cushions duration; London does not
Sophia | Extra transition (HK->Malvern->London = 2 moves vs 1) | 1 | 1 | 1 | 2 | 5 | 10 | 2 | 3 | 6 | Time the move to a school-year boundary; Malvern is near Granny (gentle first move) | [JH] She is adaptable; modest impact
Sophia | [JH] Midweek absence 3 nights/wk during the interim | 1 | 1 | 1 | 2 | 5 | 10 | 1 | 1 | 1 | Keep to 2-3 fixed nights + guaranteed weekends; she is with Granny | [JH] She is 12, mature, very close to Granny; 4 days/wk with Dad is plenty (was to be 50/50 with mother anyway). Not preferable but MANAGEABLE. Fable rated impact 4-5; JH rates 2.
Sophia / Mum | [JH] Mum (Sophia's Granny) unavailable mid-interim = single point of failure | 1 | 1 | 1 | 5 | 2 | 10 | 1 | 1 | 1 | Good health now (low prob); pre-price a paid-carer contingency; monitor health; keep a break-glass London-move plan | [JH] Real and hard to fully mitigate; manage by low current probability + contingency. Record Mum's consent + capacity.
Operational | Tenancy: cannot get vacant possession on the exit date (overstay / Renters' Rights) | 1 | 1 | 1 | 4 | 3 | 12 | 1 | 1 | 1 | Break clause; short-let or company tenant; temp-accommodation buffer at exit; solicitor check BEFORE committing | Mitigable; verify deliverability first
Operational | Duration drift: interim runs ~2yr not ~1yr (misses summer window) | 1 | 1 | 1 | 3 | 4 | 12 | - | - | - | Hard dated, tenancy-enforced move-by; any extension needs a fresh decision | See the Drift & Run-rate sheet
Career | Cannot land a good permanent role in the target lanes | 3 | 3 | 9 | 3 | 3 | 9 | 4 | 3 | 12 | Niche positioning (CCIE+CISSP+SASE); presales revenue hook; AI as differentiator | Same for both UK paths; worse in a declining HK market
Career | Best-fit hybrid roles need client-site / fixed days (breaks crash-pad + Sophia limit) | 1 | 1 | 1 | 3 | 3 | 9 | 1 | 1 | 1 | Target the flexible-hybrid subset (~25%); accept occasional full-office weeks | The interim's internal contradiction; narrows the pool, not fatal
HK / Career | TTI never converts to permanent (short-term fix only → stuck, move delayed) | - | - | - | - | - | - | 4 | 4 | 16 | Hard 17 Jul gate: written terms + conversion intent, or the move executes | P(real perm HK role via TTI) ~5-15% (Fable)
HK / Market | HK market declines further / redundancy (post-Telstra-exit context) | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 3 | 12 | Structural; pushes toward the move | A reason MOVE stays committed
Decision quality | Emotional U-turn / warm-voice drift (esp. toward staying) | 2 | 2 | 4 | 2 | 2 | 4 | 3 | 3 | 9 | Commitment-lock protocol; F-N-M-T reopen test; this register + 48h stand-down | Managed by process, not eliminated
Relationship | Joanne entanglement / relationship risk (if staying in HK) | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 9 | Prenup + Sophia inheritance ring-fence; a dated, communicated decision | Stay-branch specific
| TOTAL exposure (indicative sum of scores - lower is safer) | 49 |  |  | 92 |  |  | 76 |  |  | Indicative only - heterogeneous risks, do not over-read the sum
How to use: adjust the yellow I/P cells to YOUR judgment; the Score and colour recompute on I x P (recalc in Excel). The TOTAL is a rough exposure index, not a decision rule. The point is to SEE the trade and then mitigate the accepted risks.

## Drift & Run-rate
The drift trap and the honest run rates (Malvern crash-pad interim)
Two DIFFERENT durations matter. (A) Search duration drives POT depletion (money risk). (B) Total interim duration drives HUMAN-exposure months + school timing (the drift trap). Once employed, salary covers living + crash-pad, so the pot STOPS depleting - the drift's cost is exposure-months and a deferred London home, not runway.
A) SEARCH-PHASE pot run-rate (money risk) - honest Malvern burn £2,600/mo vs London £4,550/mo
Landing pot (liquid) | London-direct: months | Malvern-interim: months | Read
45000 | 9.9 | 17.3
50000 | 11 | 19.2 | derived pot ~£50-56k
55000 | 12.1 | 21.2 | derived pot ~£50-56k
62000 | 13.6 | 23.8 | £62k = after banking the rebate
At the derived ~£50-56k pot: London funds ~11-12mo (below a normal 12-18mo search → MPF raid); Malvern funds ~19-21mo on the honest burn. Banking the rebate (~£62k) lifts London to ~13-14mo.
B) TOTAL-INTERIM duration scenarios (the drift trap) - human-exposure months + school timing
| CLEAN (1yr, exit summer 2027) | DRIFT (2yr, exit summer 2028) | Why
Job landed by | ~month 3-4 | ~month 6-9 | Search length varies; ~25% reachable hybrid pool lengthens it
'Stable' (past probation ~6mo) | ~month 9-10 | ~month 12-15 | Stable = past probation and no PIP/redundancy risk
Next school-move window | Summer 2027 | Summer 2028 | Family moves only in Jul-Aug; a stable date after ~May misses that summer
Total interim length | ~10 months | ~22 months | The drift: a good stable job pushes the exit past the 2027 window
Sophia midweek-absence months | ~5 | ~16 | Only during the EMPLOYED phase (crash-pad running)
Mum-dependency months | ~10 | ~22 | Whole interim rests on her availability
Sophia school outcome | Year 8 in Malvern, London from Year 9 | Malvern through Year 9, London from Year 10 | Year-10 start is GCSE-options-adjacent - the near-disqualifying case
Pot at risk? | Only search phase | Only search phase | Once employed, salary covers all; drift does NOT burn the pot
KEY: the drift trap is a HUMAN-exposure + school-timing risk, not a money risk (the pot is safe once employed). The mitigation is a HARD dated move-by (Cecil let engineered to end Jun-Jul 2027), NOT more runway.