## 0. Where we are
UK RELOCATION - RAID + DECISIONS REGISTER
As of | 2026-07-12
Committed decision | MOVE Hong Kong -> UK (committed 4 Jul, BRAINED + Fable-reviewed). Reopen only via the F-N-M-T test.
Live sub-decision | WHERE to land: London-direct vs Malvern crash-pad interim vs Stay-HK (TTI lifeline).
Current position | A genuine trade. Fable's red-team + the tight ~£50-56k pot made London-direct the pragmatic default; but Julian's judgment + the 12 Jul Cecil decision materially de-risk the interim (tenancy + drift now LOW; Sophia-midweek judged manageable; Mum-SPOF low-prob + contingency). So the interim is more viable than the red-team's demotion implied. It is now Julian's judgment call - this register is the tool.
The live question | Does Julian judge the interim's residual human risks (Sophia-midweek, Mum-SPOF) as acceptable and lower than London-direct's money-risk of a tight-pot search? If yes -> interim (bounded to Aug 2027). If no -> London-direct + aggressive runway mitigation.
Key numbers | Pot ~£50-56k (banking the £12,475 rebate -> ~£62-69k). Search runway: London ~11-12mo vs Malvern ~19-21mo (honest £2,600 burn). Cecil freed / interim exit anchored Aug 2027.
Top open items | TTI answer by 17 Jul; bank the rebate; record Mum's consent; confirm best-fit hybrid roles tolerate 2-3 fixed nights; secure a Malvern in-year school place; retype the committed choice.

## 1. Decisions
ID | Date | Decision | Status | Rationale | Reopen/review condition
DEC-1 | 2026-07-04 | MOVE Hong Kong -> UK | COMMITTED | BRAINED analysis + Fable review; gut-override failed on 3 grounds | Reopen only via F-N-M-T + 48h stand-down
DEC-2 | 2026-07-07 | Land London-direct (live in Cecil Road) | OPEN / CONTESTED | Chosen 7 Jul; reopened 10 Jul on corrected finances; now a live 3-way trade | Resolves when Julian makes the judgment call
DEC-3 | 2026-07-12 | Cecil Road: keep existing happy tenants; fair notice timed for an Aug 2027 move | DECIDED | De-risks the tenancy kill-shot and anchors the interim exit to Aug 2027 (kills the drift trap; clean Year-9 London start) | Confirm tenants accept the Aug 2027 notice
DEC-4 | 2026-07-11 | Malvern permanent RESIDENT base is ruled out | CLOSED | Job pool ~15% of London for a resident; only the crash-pad interim (reaching London hybrid) is viable on the Malvern side | -
DEC-5 | pending | Retype the committed choice in Julian's own words | OUTSTANDING | Lock-protocol condition; the cheapest gate and the only test of H3 | Do before any LOCK
DEC-6 | 2026-07-10 | TTI = pre-registered Branch A, time-boxed | OPEN | A credible permanent-HK on-ramp would favour staying; hard 17 Jul deadline | Written terms + conversion intent by 17 Jul, or move executes

## 2. Risks
CECIL DECISION (JH, 12 Jul): keep existing happy tenants; give fair notice timed for an Aug 2027 move. This de-risks the tenancy row and ANCHORS the interim exit to Aug 2027 (kills the drift trap; Sophia gets a clean Year-9 London start). Implication: 'London-direct now' would need paid London rent until Cecil frees Aug 2027, so the Malvern interim is the natural bridge.
Category | Risk | London-direct: I | London-direct: P | London-direct: Score | London-direct: RAG | Malvern crash-pad interim: I | Malvern crash-pad interim: P | Malvern crash-pad interim: Score | Malvern crash-pad interim: RAG | Stay-HK (TTI lifeline): I | Stay-HK (TTI lifeline): P | Stay-HK (TTI lifeline): Score | Stay-HK (TTI lifeline): RAG | Key mitigation | Residual / Julian judgment
Financial | Run out of money in search -> forced early pension/MPF drawdown | 4 | 4 | 16 | RED | 4 | 2 | 8 | AMBER | 2 | 2 | 4 | GREEN | Bank the 12,475 rebate; floor job early ~77k; MPF backstop | London's central risk (tight ~50-56k pot, ~11-12mo); Malvern runway defuses it
Financial | Long search at 55 (ageism) outlasts the runway | 4 | 3 | 12 | AMBER | 3 | 2 | 6 | GREEN | 2 | 2 | 4 | GREEN | Niche-lane discipline; long Malvern runway; take a floor job then trade up | Malvern cushions duration; London does not
Sophia | Extra transition (HK->Malvern->London = 2 moves vs 1) | 1 | 1 | 1 | GREEN | 2 | 4 | 8 | AMBER | 2 | 3 | 6 | GREEN | Move at a school-year boundary; Malvern is near Granny (gentle first move) | [JH] She is adaptable; modest impact
Sophia | [JH] Midweek absence 3 nights/wk during the interim | 1 | 1 | 1 | GREEN | 2 | 5 | 10 | AMBER | 1 | 1 | 1 | GREEN | Keep to 2-3 fixed nights + guaranteed weekends; she is with Granny | [JH] 12, mature, very close to Granny; 4 days/wk with Dad is plenty (was to be 50/50 with mother). Not preferable but MANAGEABLE. Fable rated 4-5; JH rates impact 2.
Sophia / Mum | [JH] Mum (Granny) unavailable mid-interim = single point of failure | 1 | 1 | 1 | GREEN | 5 | 2 | 10 | AMBER | 1 | 1 | 1 | GREEN | Low prob now (good health); pre-price a paid-carer contingency; monitor health; keep a break-glass London-move plan; record Mum's consent | [JH] Real, hard to fully mitigate; manage via low current probability + contingency
Operational | Tenancy: cannot get vacant possession on the exit date | 1 | 1 | 1 | GREEN | 3 | 1 | 3 | GREEN | 1 | 1 | 1 | GREEN | DECIDED (JH): keep existing happy tenants; fair Renters-Rights-compliant notice timed for Aug 2027. Vacant possession by agreement | [JH] Largely mitigated by the Cecil decision; low residual
Operational | Duration drift: interim runs ~2yr not ~1yr | 1 | 1 | 1 | GREEN | 2 | 2 | 4 | GREEN | - | - | - |  | ANCHORED (JH): Cecil notice timed for Aug 2027 = a hard, date-driven move-by; kills 'stable + year-end' slippage | [JH] Residual: if no job by Aug 2027, family moves to London still searching (higher burn) - but after ~9mo cheap search. Bounded, acceptable
Career | Cannot land a good permanent role in the target lanes | 3 | 3 | 9 | AMBER | 3 | 3 | 9 | AMBER | 4 | 3 | 12 | AMBER | Niche positioning (CCIE+CISSP+SASE); presales revenue hook; AI differentiator | Same both UK paths; worse in a declining HK market
Career | Best-fit hybrid roles need client-site / fixed days (breaks crash-pad) | 1 | 1 | 1 | GREEN | 3 | 3 | 9 | AMBER | 1 | 1 | 1 | GREEN | Target the flexible-hybrid subset (~25%); accept occasional full-office weeks | The interim's internal contradiction; narrows the pool, not fatal
HK / Career | TTI never converts to permanent (short-term fix only -> stuck) | - | - | - |  | - | - | - |  | 4 | 4 | 16 | RED | Hard 17 Jul gate: written terms + conversion intent, or the move executes | P(real perm HK role via TTI) ~5-15%
HK / Market | HK market declines further / redundancy | 1 | 1 | 1 | GREEN | 1 | 1 | 1 | GREEN | 4 | 3 | 12 | AMBER | Structural; pushes toward the move | A reason MOVE stays committed
Decision quality | Emotional U-turn / warm-voice drift (esp. toward staying) | 2 | 2 | 4 | GREEN | 2 | 2 | 4 | GREEN | 3 | 3 | 9 | AMBER | Commitment-lock protocol; F-N-M-T; this register; 48h stand-down | Managed by process, not eliminated
Relationship | Joanne entanglement / relationship risk (if staying) | 1 | 1 | 1 | GREEN | 1 | 1 | 1 | GREEN | 3 | 3 | 9 | AMBER | Prenup + Sophia inheritance ring-fence; a dated, communicated decision | Stay-branch specific
| TOTAL exposure (indicative - lower safer) |  |  | 49 |  |  |  | 73 |  |  |  | 76 |  | Crude sum; Malvern high mainly = more line-items; weigh the single RED cells

## 3. Assumptions
ID | Assumption | Confidence | Basis | Validated? | Impact if wrong
A1 | BFSI experience counts as sector experience (not 'must have worked for a bank') | Med | target-role-profile; bank-embedded BT/AT&T/Telstra work | Mixed, leans holds | Narrows BFSI perm/contract roles
A2 | Age is a secondary, not core, mover | Med-High | Equality Act vs HK; but UK tech ageism endemic | Holds (legal delta real, hiring delta unproven) | Would weaken a pro-UK pillar (already secondary)
A3 | Niche-lane scarcity (CCIE+CISSP+SASE+presales) is real | Low | Asserted; recruiter to confirm; pool est 14-429 (30x range) | UNVALIDATED | If pool is deep, the UK market-size edge shrinks toward a wash
A4 | Clearable long-term via sponsored-SC perm (not near-term DV contract) | Med | GOV.UK residency rules + Adzuna cleared roles | Holds with caveat | Cleared lane slips further out
A5 | Landing pot ~£50-56k | Med | Derived from £91,869 non-ISA liquid (financial-model §10) | Derived; swing on rebate timing + one-offs | If <£45k, interim case strengthens; if topped up, London eases
A6 | Honest Malvern search burn ~£2,600/mo | Med | §9b: adds board + car + schooling to the £1,683 base | Estimate, to firm | Runway edge shrinks if higher
A7 | ~25% of London roles are genuinely crash-pad-compatible | Low-Med | Adzuna text-inference, minus fixed-day/client-site | Directional | If lower, the interim's job-access edge weakens
A8 | Mum is healthy, willing and able to cover Sophia for the interim | Low (unrecorded) | Julian's read; her consent/capacity not yet recorded | UNVALIDATED | Collapses the interim's childcare + burn spine
A9 | Cecil tenants happy to stay and will leave on fair Aug 2027 notice | Med | Julian's assertion (12 Jul) | To confirm with tenants | Undermines the interim exit anchor
A10 | A floor job ~£77k is high-probability (over-qualified) | Med-High | feasibility report | Holds | London runway mitigation weakens if wrong
A11 | HK PR retained with ~3-yearly visits; MPF withdrawal does not affect PR | High | Immigration lawyer via Justin | Confirmed | -

## 4. Dependencies
ID | Dependency | Type | Due | Status | Blocks
DEP-1 | TTI: written terms + conversion intent | External (Stephan/Ty/Horst) | 17 Jul | Open | The Stay-HK branch; the location decision timing
DEP-2 | MPF withdrawal timing vs UK tax residency + tax adviser | External/Action | Before departure | Open | Departure logistics; ~£124.5k buffer + mortgage payoff
DEP-3 | Cecil tenants accept an Aug 2027 notice | External | Soon | Open | The interim exit anchor / drift mitigation
DEP-4 | School places (Malvern in-year for interim; London Sept 2027) | External/Action | Rolling | Open | Sophia's timeline under the interim
DEP-5 | Mum's consent + capacity to cover Sophia | External | Before choosing interim | Open | The interim's childcare + low-burn spine
DEP-6 | Bank the £12,475 tax rebate before departure | Action | Before departure | Open | Improves the pot to ~£62-69k
DEP-7 | Firm shipping quote | Action | Soon | Open | Firms the pot one-offs (±£5k)
DEP-8 | DB flat consent-to-let (HSBC) | External | Soon | Open | DB rental income (~£970/mo cash cost either way)

## 5. Issues
ID | Issue | Severity | Status | Action
ISS-1 | Landing pot was un-derived | Was High | RESOLVED (12 Jul) | Derived ~£50-56k in financial-model §10
ISS-2 | '87% contract' arithmetic error propagated across 4 docs | Low | RESOLVED | Corrected to 85% (68/80) everywhere
ISS-3 | Report over-claimed 'Malvern cannot reach London hybrid' | Med | RESOLVED | Crash-pad correction folded in; ~25% planning figure
ISS-4 | Malvern burn under-costed (£1,683 vs honest ~£2,600) | Med | RESOLVED | Added §9b hostile costing
ISS-5 | Sophia needs a Malvern in-year school place for a ~1yr interim stint | Med | OPEN | Secure an in-year state place; feeds DEP-4
ISS-6 | Mum's consent and capacity are unrecorded | Med-High | OPEN | Have the conversation; record it (feeds A8/DEP-5)
ISS-7 | Do best-fit presales/hybrid roles tolerate 2-3 fixed nights? | Med | OPEN | Test against live JDs; the interim's internal contradiction
ISS-8 | Retype-the-choice lock item outstanding | Low-Med | OPEN | Julian to write the committed choice in his own words
ISS-9 | Tenant-overstay legal risk (Renters' Rights) | Low now | MITIGATED | Cecil decision (happy sitting tenants); verify notice mechanics with a solicitor

## 6. Drift & Run-rate
DRIFT & RUN-RATE
A) SEARCH-PHASE pot run-rate (money) - honest burn: Malvern 2,600/mo vs London 4,550/mo
Landing pot | London-direct: months | Malvern-interim: months | Read
45000 | 9.9 | 17.3
50000 | 11.0 | 19.2 | derived pot ~50-56k
55000 | 12.1 | 21.2 | derived pot ~50-56k
62000 | 13.6 | 23.8 | after banking the rebate
B) INTERIM-DURATION (the drift trap) - human-exposure + school timing. NOTE: pot is safe once employed; drift cost = exposure months, not money
| CLEAN (1yr, exit Aug 2027 - now ANCHORED) | DRIFT (2yr) - now largely blocked by the Cecil Aug-2027 anchor | Why
Total interim length | ~10 months | ~22 months | Cecil notice timed for Aug 2027 forces the clean case
Sophia midweek-absence months | ~5 | ~16 | Only during the employed phase
Mum-dependency months | ~10 | ~22 | Whole interim rests on her availability
Sophia school outcome | Year 8 Malvern, London from Year 9 | London from Year 10 (GCSE-adjacent) | The Aug-2027 anchor delivers the Year-9 clean case